## Summary
Hamro Mall Admin Platform – Work Breakdown Structure
Based on SRS Vol.1 (Product, Attributes, Order, Vendors) and Vol.2 (Customer, Role, CMS, Settings). Hours = effort hours.
Assumptions (blue = editable input)
Contingency % |  | 10%
Productive hours per person-week |  | 35
Team size (people working in parallel) |  | 6
Base effort (hrs) |  | 3215
Effort incl. contingency (hrs) |  | 3536.5
Person-weeks |  | 101.0429
Indicative duration (weeks, if team works fully parallel) |  | 16.8405
Effort by Epic
ID | Name | Stories | Frontend | Backend | QA | DevOps | Total | % of total
E01 | Project Setup & Platform Foundation | 5 | 44 | 76 | 26 | 32 | 178 | 5.537%
E02 | Authentication, RBAC & Role Management | 13 | 120 | 144 | 75 | 0 | 339 | 10.54%
E03 | Admin Shell & Notifications | 5 | 58 | 26 | 21 | 0 | 105 | 3.266%
E04 | Master Data (Category, Brand, Warehouse, Lists) | 4 | 52 | 42 | 22 | 0 | 116 | 3.608%
E05 | Attributes | 3 | 30 | 26 | 15 | 0 | 71 | 2.208%
E06 | Product – Add Product Wizard | 16 | 202 | 98 | 81 | 0 | 381 | 11.85%
E07 | Product – Product List | 6 | 76 | 68 | 36 | 0 | 180 | 5.599%
E08 | Product – Expire Product | 6 | 46 | 68 | 30 | 0 | 144 | 4.479%
E09 | Order Management | 8 | 88 | 112 | 50 | 0 | 250 | 7.776%
E10 | Vendor Management | 6 | 68 | 66 | 35 | 0 | 169 | 5.257%
E11 | Customer Management | 8 | 56 | 68 | 33 | 0 | 157 | 4.883%
E12 | CMS – Web Management & Media | 21 | 258 | 204 | 113 | 0 | 575 | 17.88%
E13 | Settings (General, Policy, Security, Currency, Subscriber) | 6 | 70 | 66 | 32 | 0 | 168 | 5.226%
E14 | Non-Functional Hardening, Testing & Release | 7 | 104 | 124 | 118 | 36 | 382 | 11.88%
| TOTAL | 114 | 1272 | 1188 | 687 | 68 | 3215 | 100%
Effort by Priority
Key | Name | Stories | Frontend | Backend | QA | DevOps | Total | % of total
Must | Must have (R1 – MVP) | 81 | 872 | 838 | 469 | 68 | 2247 | 69.89%
Should | Should have (R2) | 25 | 300 | 258 | 174 | 0 | 732 | 22.77%
Could | Could have (R3) | 8 | 100 | 92 | 44 | 0 | 236 | 7.341%
| TOTAL | 114 | 1272 | 1188 | 687 | 68 | 3215 | 100%
Notes
1. Estimates are for a mid-level engineer, include developer unit tests, and are accurate to about ±20%. QA hours include test design and execution.
2. Priority follows the SRS MoSCoW. Release: Must = R1 (MVP), Should = R2, Could = R3.
3. Frontend / Backend / QA / DevOps hours are shown separately; Developer Role(s) lists every role with hours on that story.
4. UI/UX design time is excluded because the FE design already exists. Findings F-01 to F-13 from the SRS are folded into the relevant stories.
5. Stories marked Dependency, provisional or scope to confirm (Category, Brand, Warehouse, Manage Users, Khalti/eSewa, non-supplied CMS pages, Policy/Security/Currency/Subscriber) need client confirmation.
6. Out of scope: customer storefront, Delivery Management, Suppliers, Delivery Rider and the Warehouse module beyond master data.
7. Change the blue inputs above to see duration update; all totals are formulas driven from the WBS sheet.

## WBS
Epic ID | Epic | Story ID | User Story | Acceptance Criteria | Priority | Release | Developer Role(s) | Frontend Hrs | Backend Hrs | QA Hrs | DevOps Hrs | Total Hrs | SRS Reference | Depends On
E01 | Project Setup & Platform Foundation | US-1.01 | As a developer, I want a Git repository with CI/CD and dev/staging/production environments so that code is built, tested and deployed consistently. | 1. Merge to develop triggers build, lint, tests and auto-deploy to staging 2. Three environments run with separate configuration and secrets 3. Rollback to previous release works in under 15 minutes | Must | R1 – MVP | Backend Dev, QA Engineer, DevOps Engineer | 0 | 4 | 2 | 24 | 30 | NFR-04, NFR-10
E01 | Project Setup & Platform Foundation | US-1.02 | As a developer, I want solution architecture, database baseline, API conventions and OpenAPI documentation so that all modules follow one consistent technical design. | 1. ERD covers all entities in SRS sections 5 2. REST conventions (pagination, error format, filtering) are documented and applied 3. Swagger/OpenAPI is generated and published for dev team | Must | R1 – MVP | Backend Dev, QA Engineer | 0 | 28 | 4 | 0 | 32 | SRS §5, NFR-10
E01 | Project Setup & Platform Foundation | US-1.03 | As a frontend developer, I want a React app scaffold with design tokens and a reusable component library (table toolbar, modal, upload zone, toast, breadcrumb, status toggle) so that every screen looks and behaves consistently. | 1. Purple theme, typography and spacing tokens match the FE design 2. Components are documented in Storybook (or equivalent) 3. Table toolbar supports search, filter, sort and primary action slots | Must | R1 – MVP | Frontend Dev, QA Engineer | 44 | 0 | 6 | 0 | 50 | FR-GLB-06, NFR-05 | 1.01
E01 | Project Setup & Platform Foundation | US-1.04 | As a platform operator, I want a file storage service with upload API, type/size validation and malware scan so that products, vendors and CMS files are stored securely. | 1. Uploads accept only allowed types and sizes and are renamed on storage 2. Infected or invalid files are rejected with a clear error 3. Returned file has URL, path, MIME type, extension and size | Must | R1 – MVP | Backend Dev, QA Engineer, DevOps Engineer | 0 | 24 | 8 | 8 | 40 | FR-MED-05, NFR-02 | 1.01
E01 | Project Setup & Platform Foundation | US-1.05 | As an admin, I want a central audit log service so that create, update, delete and status changes are traceable. | 1. Each audited action stores user, entity, action, before/after values, IP and timestamp 2. Audit entries cannot be edited or deleted from the UI 3. Logs are retained for 12 months | Must | R1 – MVP | Backend Dev, QA Engineer | 0 | 20 | 6 | 0 | 26 | NFR-08, BR-08 | 1.02
E02 | Authentication, RBAC & Role Management | US-2.01 | As an admin user, I want to log in and out securely with a session timeout so that only authorised staff access the panel. | 1. Valid credentials open the dashboard; invalid credentials show an error 2. Session expires after configured inactivity and redirects to login 3. Passwords are hashed; brute-force attempts are throttled | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 20 | 8 | 0 | 40 | Dependency (auth out of SRS scope) | 1.02
E02 | Authentication, RBAC & Role Management | US-2.02 | As a super admin, I want permissions enforced on both menu and API so that users see and do only what their role allows. | 1. Menu items and buttons without permission are hidden 2. API returns 403 for unauthorised calls even if the UI is bypassed 3. Permission changes apply on next request or login | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 24 | 10 | 0 | 46 | FR-GLB-05, NFR-01 | 2.10
E02 | Authentication, RBAC & Role Management | US-2.03 | As an admin, I want to view and search all roles in a table so that I can find and manage roles quickly. | 1. Table shows S.N, Role Name, Description, Status toggle and view/edit/delete icons 2. Search filters by name and description as I type 3. Empty result shows "No roles found" | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 8 | 6 | 0 | 26 | FR-ROL-01, 02 | 1.03
E02 | Authentication, RBAC & Role Management | US-2.04 | As an admin, I want to add a role with name and description so that new staff types can be created. | 1. Role Name is required, unique (case-insensitive), 2–50 characters 2. Description is optional, up to 255 characters 3. New role is Active and appears in the list without page reload | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 5 | 0 | 21 | FR-ROL-03 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.05 | As an admin, I want to edit a role so that role details stay correct. | 1. Dialog pre-fills current name and description 2. Same validation as Add applies 3. Save updates the table row and shows a success toast | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 6 | 6 | 4 | 0 | 16 | FR-ROL-04 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.06 | As an admin, I want to view role details in a read-only dialog so that I can check a role without editing it. | 1. Eye icon opens dialog with icon, name, ACTIVE/INACTIVE badge and description 2. Dialog closes with the x icon or Esc | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 2 | 2 | 0 | 8 | FR-ROL-05 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.07 | As an admin, I want to delete a role after confirmation so that unused roles are removed. | 1. Confirmation quotes the role name and states the action cannot be undone 2. A role assigned to users cannot be deleted; message shows the user count 3. Successful delete removes the row and logs an audit entry | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 6 | 8 | 5 | 0 | 19 | FR-ROL-06, 07, BR-03 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.08 | As a super admin, I want the Admin role to be protected so that the system can never lose full access. | 1. Admin cannot be deleted or deactivated from UI or API 2. Admin permissions cannot be reduced | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 2 | 6 | 3 | 0 | 11 | FR-ROL-08, BR-02 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.09 | As an admin, I want to activate or deactivate a role with a toggle so that I can pause a role without deleting it. | 1. Toggle updates status immediately with a toast 2. Inactive roles cannot be assigned to new users 3. Behaviour for existing users is applied as confirmed by the client (open question) | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 4 | 3 | 0 | 11 | FR-ROL-09 | 2.03
E02 | Authentication, RBAC & Role Management | US-2.10 | As a super admin, I want a permission matrix per role (modules × View/Create/Edit/Delete/Export) so that each role has exact access rights. | 1. Edit Role has a Manage Permissions tab listing all modules and actions 2. Saving stores permissions and enforces them via 2.02 3. Select-all per module and per action is available | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 24 | 24 | 12 | 0 | 60 | FR-ROL-11 (gap) | 2.04
E02 | Authentication, RBAC & Role Management | US-2.11 | As an admin, I want to select multiple roles and apply bulk actions so that repetitive changes are faster. | 1. Header checkbox selects all rows on the page 2. Bulk activate, deactivate and delete work with confirmation 3. Admin role is excluded from bulk delete | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 4 | 0 | 20 | FR-ROL-10 | 2.07
E02 | Authentication, RBAC & Role Management | US-2.12 | As an admin, I want role changes written to the audit log so that changes can be reviewed. | 1. Create, update, status change and delete are logged with before/after values 2. Audit entries are viewable by Admin only | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 2 | 6 | 3 | 0 | 11 | FR-ROL-12 | 1.05
E02 | Authentication, RBAC & Role Management | US-2.13 | As an admin, I want to create staff users and assign them a role (Manage Users) so that roles take effect for real people. | 1. User form has name, email, phone, role, status 2. Only active roles are selectable 3. User list supports search, filter and sort | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 20 | 10 | 0 | 50 | Manage Users menu (scope to confirm) | 2.04
E03 | Admin Shell & Notifications | US-3.01 | As an admin, I want a collapsible sidebar with grouped menus so that I can navigate all modules. | 1. Groups Order Management, Users, CMS, Settings and items match the FE design 2. Active item is highlighted; expandable groups show chevron 3. Sidebar scrolls independently and collapses via arrow | Must | R1 – MVP | Frontend Dev, QA Engineer | 16 | 0 | 4 | 0 | 20 | FR-GLB-01, 02 | 1.03
E03 | Admin Shell & Notifications | US-3.02 | As an admin, I want a header with full-screen toggle, notification bell and profile menu so that common tools are always available. | 1. Bell shows unread count capped at "99+" 2. Full-screen toggles and exits correctly 3. Profile menu has profile and logout | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 2 | 4 | 0 | 16 | FR-GLB-03 | 1.03
E03 | Admin Shell & Notifications | US-3.03 | As an admin, I want breadcrumbs and page titles on every page so that I always know where I am. | 1. Format is Home > Section > Page 2. Breadcrumb parents are clickable and match menu hierarchy (fixes F-01, F-08) | Must | R1 – MVP | Frontend Dev, QA Engineer | 4 | 0 | 2 | 0 | 6 | FR-GLB-04 | 1.03
E03 | Admin Shell & Notifications | US-3.04 | As an admin, I want consistent toasts, confirmation dialogs and inline validation so that I get clear feedback on every action. | 1. Required fields show red asterisk and inline error on submit 2. Destructive actions require confirmation 3. Success and error toasts auto-dismiss | Must | R1 – MVP | Frontend Dev, QA Engineer | 8 | 0 | 3 | 0 | 11 | FR-GLB-07, 08 | 1.03
E03 | Admin Shell & Notifications | US-3.05 | As an admin, I want a notification centre for low stock, expiry, new orders and vendor submissions so that I act on events without checking each module. | 1. Events create notifications with type, text, time and deep link 2. Bell count updates; mark read and mark all read work 3. Low-stock alert fires when stock ≤ threshold | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 20 | 24 | 8 | 0 | 52 | FR-PRD-021, FR-EXP-005, F-13 | 2.01
E04 | Master Data (Category, Brand, Warehouse, Lists) | US-4.01 | As a catalogue manager, I want to manage product categories (hierarchical) so that products are organised for the storefront. | 1. Create, edit, deactivate categories with parent/child 2. Category cannot be deleted while products use it 3. Active categories feed the Add Product dropdown | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 16 | 8 | 0 | 44 | FR-PRD-002 (dependency) | 1.03
E04 | Master Data (Category, Brand, Warehouse, Lists) | US-4.02 | As a catalogue manager, I want to manage brands so that products can be branded. | 1. Create, edit, deactivate brands with logo 2. Brand in use cannot be deleted 3. Active brands feed the Add Product dropdown | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 8 | 5 | 0 | 25 | FR-PRD-002 (dependency) | 1.03
E04 | Master Data (Category, Brand, Warehouse, Lists) | US-4.03 | As an operations manager, I want to manage warehouses so that stock is tracked by location. | 1. Create, edit, deactivate warehouses with name, address, contact 2. Active warehouses are selectable in pricing & inventory step | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 10 | 5 | 0 | 27 | FR-PRD-020 (dependency) | 1.03
E04 | Master Data (Category, Brand, Warehouse, Lists) | US-4.04 | As a catalogue manager, I want configurable lists for shipping class, return period and warranty period so that product policies are consistent. | 1. Lists are editable by authorised users 2. Add Product step 3 reads values from these lists | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 4 | 0 | 20 | FR-PRD-022, 023 | 1.03
E05 | Attributes | US-5.01 | As a catalogue manager, I want to create, edit and deactivate attributes with name and unique code so that variants can be built from them. | 1. Attribute Code is unique; duplicates show an error 2. List supports search and pagination 3. Created attributes are immediately selectable | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-ATT-001 | 1.03
E05 | Attributes | US-5.02 | As a catalogue manager, I want to manage attribute values (S, M, L; Red, Grey, Brown) so that products can use standard values. | 1. Values can be added, edited, ordered and removed per attribute 2. Duplicate values within an attribute are rejected | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 8 | 5 | 0 | 25 | FR-ATT-001 | 5.01
E05 | Attributes | US-5.03 | As a catalogue manager, I want attributes and values in use to be protected from deletion so that live products are not broken. | 1. Delete is blocked when used by products and message shows usage count 2. Deactivate option is offered instead | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 8 | 4 | 0 | 16 | FR-ATT-002 | 5.01
E06 | Product – Add Product Wizard | US-6.01 | As a catalogue manager, I want a 4-step Add Product wizard with progress, checklist and Previous/Next/Cancel so that I can create a product step by step. | 1. Progress shows "Completion n/4" and updates per step 2. Previous keeps entered data; Cancel asks for confirmation 3. Failing step is highlighted when validation fails | Must | R1 – MVP | Frontend Dev, QA Engineer | 24 | 0 | 6 | 0 | 30 | §3.1, FR-PRD-035 | 1.03
E06 | Product – Add Product Wizard | US-6.02 | As a catalogue manager, I want to enter name, category, brand, short and full description so that the product is identified clearly. | 1. Name, Category and Brand are mandatory 2. Dropdowns load from master data 3. Short description is shown in listings | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 6 | 5 | 0 | 23 | FR-PRD-001, 002, 004 | 4.01
E06 | Product – Add Product Wizard | US-6.03 | As a catalogue manager, I want to upload up to 20 images/videos by drag-drop or browse so that the product has rich media. | 1. PNG, JPG, WEBP, GIF, MP4 up to 50 MB each; 21st file is rejected 2. Thumbnails show with remove and reorder 3. Upload progress and errors are displayed | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 16 | 10 | 6 | 0 | 32 | FR-PRD-003 | 1.04
E06 | Product – Add Product Wizard | US-6.04 | As a system, I want to auto-generate a UUID and display ID (PROD-000xxx) so that every product is uniquely identifiable. | 1. IDs are generated on first save and never change 2. Display IDs are sequential and unique | Must | R1 – MVP | Backend Dev, QA Engineer | 0 | 6 | 2 | 0 | 8 | FR-PRD-006 | 1.02
E06 | Product – Add Product Wizard | US-6.05 | As a catalogue manager, I want a live preview panel with Draft badge, name, image, category, price and stock so that I see how the product will look. | 1. Preview updates in real time as I type 2. Placeholder image shown when no image 3. "Rs x" price and "n in stock" badge reflect entered values | Should | R2 | Frontend Dev, QA Engineer | 16 | 0 | 4 | 0 | 20 | FR-PRD-005, 024 | 6.02
E06 | Product – Add Product Wizard | US-6.06 | As a catalogue manager, I want to pick attributes and their values as chips so that I define product options. | 1. Searchable multi-select of attributes; at least one required 2. Selecting an attribute shows its values as selectable chips 3. Each attribute block can be removed | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 6 | 6 | 0 | 32 | FR-PRD-010, 011 | 5.02
E06 | Product – Add Product Wizard | US-6.07 | As a catalogue manager, I want to create a new attribute from inside the wizard so that I do not leave my work. | 1. "New Attributes" opens modal with Name* and unique Code* 2. On Create the attribute is selectable immediately | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 2 | 3 | 0 | 13 | FR-PRD-012, FR-ATT-003 | 5.01
E06 | Product – Add Product Wizard | US-6.08 | As a catalogue manager, I want a toggle to enable variant management and auto-generate combinations so that all variants are created without manual work. | 1. ON generates the Cartesian product of selected values 2. OFF treats product as simple single-SKU and step 3 captures price/stock 3. Helper text shows when no values selected | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 10 | 8 | 0 | 38 | FR-PRD-013, 015, 016 | 6.06
E06 | Product – Add Product Wizard | US-6.09 | As a catalogue manager, I want SKU, price, stock and image per variant so that each variant sells independently. | 1. SKU is unique across the system 2. Variant stock rolls up to product stock 3. Optional image per variant | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 14 | 8 | 0 | 42 | FR-PRD-014, BR-03 | 6.08
E06 | Product – Add Product Wizard | US-6.10 | As a catalogue manager, I want to set price, discount, stock, warehouse and low-stock threshold so that pricing and inventory are correct. | 1. Discount accepts % or amount and cannot exceed price; final price ≥ 0 2. Low-stock threshold is mandatory with default 10 3. Stock is stored per warehouse | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-PRD-020, 021, BR-04 | 4.03
E06 | Product – Add Product Wizard | US-6.11 | As a catalogue manager, I want to enter shipping dimensions, class, return and warranty periods so that delivery and policy info is complete. | 1. Weight (kg) and L/W/H (cm) accept numbers only 2. Shipping class, return period and warranty period are mandatory dropdowns | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 4 | 4 | 0 | 16 | FR-PRD-022, 023 | 4.04
E06 | Product – Add Product Wizard | US-6.12 | As a catalogue manager, I want Meta Title, Meta Description and a unique URL slug so that the product ranks in search. | 1. Meta Title is required; slug is required, lowercase, hyphenated and auto-suggested from the name 2. Duplicate slug shows an error | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 6 | 5 | 0 | 21 | FR-PRD-030, 031, BR-02 | 6.02
E06 | Product – Add Product Wizard | US-6.13 | As a catalogue manager, I want an SEO score and Google search preview so that I can optimise listings. | 1. Score 0–100 reaches 100 only when all checks pass 2. Preview shows title, URL breadcrumb and description with real store domain | Should | R2 | Frontend Dev, QA Engineer | 14 | 0 | 4 | 0 | 18 | FR-PRD-032, 033 | 6.12
E06 | Product – Add Product Wizard | US-6.14 | As a catalogue manager, I want Featured and New Arrival flags so that marketing can highlight products. | 1. Both checkboxes save and flow to product list and storefront | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 2 | 2 | 2 | 0 | 6 | FR-PRD-034 | 6.01
E06 | Product – Add Product Wizard | US-6.15 | As a catalogue manager, I want Publish Product to validate all steps so that only complete products go live. | 1. Publish is blocked with failing step highlighted if any BR-01 field is missing 2. Product of a non-approved vendor cannot be published 3. Success sets status Published and logs audit entry | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 14 | 8 | 0 | 32 | FR-PRD-035, BR-01, BR-06 | 10.05
E06 | Product – Add Product Wizard | US-6.16 | As a catalogue manager, I want to save a draft and resume later so that I do not lose partial work. | 1. Save as Draft stores incomplete data 2. Draft appears in Draft tab and reopens at last step | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 4 | 0 | 20 | FR-PRD-036 | 6.01
E07 | Product – Product List | US-7.01 | As a catalogue manager, I want a paginated product table with tabs (All, Digital, Physical, Draft) so that I can review the catalogue. | 1. Columns match SRS: thumbnail, ID, name/brand, category, ratings, price/discount, units sold, toggles, action 2. Draft tab lists only unpublished products 3. Add Product button opens the wizard | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 24 | 16 | 8 | 0 | 48 | FR-PL-001, 007, 008 | 6.01
E07 | Product – Product List | US-7.02 | As a catalogue manager, I want to search, filter and sort products so that I find items fast. | 1. Search by name, ID, brand 2. Filter by category, brand, status, owner, price range 3. Sort ascending/descending | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 12 | 6 | 0 | 30 | FR-PL-002 | 7.01
E07 | Product – Product List | US-7.03 | As a catalogue manager, I want inline Published, Featured and Today's Deal toggles so that I update visibility in one click. | 1. Toggle persists immediately with toast and audit entry 2. Failed save reverts toggle and shows error | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 5 | 0 | 21 | FR-PL-003 | 1.05
E07 | Product – Product List | US-7.04 | As a catalogue manager, I want Edit Info, Edit Attributes, View and Delete in the action menu so that I can maintain products. | 1. Edit opens the wizard prefilled at the right step 2. Delete asks confirmation and is a soft delete 3. View shows read-only product detail | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 16 | 12 | 8 | 0 | 36 | FR-PL-004, BR-08 | 6.01
E07 | Product – Product List | US-7.05 | As a catalogue manager, I want bulk Export All and Delete Selected so that I handle many products at once. | 1. Export downloads CSV/XLSX of current filter 2. Delete Selected is disabled until rows are selected | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 6 | 12 | 5 | 0 | 23 | FR-PL-005 | 7.01
E07 | Product – Product List | US-7.06 | As a catalogue manager, I want a View Stock link showing stock per warehouse and variant so that I can check inventory. | 1. Popup lists warehouse, variant, quantity | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 10 | 8 | 4 | 0 | 22 | FR-PL-006 | 7.01
E08 | Product – Expire Product | US-8.01 | As a catalogue manager, I want a table of products by expiry (No., Product, Category, Stock Left, Created, Days Left, Status, Action) so that I see what is expiring. | 1. Breadcrumb Home > Product Management > Product > Expire Product 2. Pagination and empty state work | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 10 | 5 | 0 | 27 | FR-EXP-001 | 6.15
E08 | Product – Expire Product | US-8.02 | As a catalogue manager, I want colour-coded Safe / Near Expiry / Expired status so that I spot risks at a glance. | 1. Status derived from Days Left; Safe > 14 days (configurable) 2. Colours match design | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 8 | 4 | 0 | 16 | FR-EXP-002 | 8.01
E08 | Product – Expire Product | US-8.03 | As a catalogue manager, I want View Details, Update Stock, Mark Reviewed and Archive actions so that expiring stock is handled. | 1. Archive removes product from sale 2. Super Admin can restore archived products 3. Each action is audited | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 14 | 7 | 0 | 35 | FR-EXP-003 | 8.01
E08 | Product – Expire Product | US-8.04 | As a catalogue manager, I want search, filter, sort, export and bulk delete on the expiry table so that I manage lots quickly. | 1. All controls behave as in product list 2. Bulk delete needs confirmation | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 4 | 0 | 20 | FR-EXP-004 | 8.01
E08 | Product – Expire Product | US-8.05 | As a catalogue manager, I want an expiry date captured at product or batch level so that expiry is accurate, not guessed from Created date. | 1. Expiry date field exists in product/stock entry 2. Days Left uses expiry date only | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 12 | 5 | 0 | 25 | FR-EXP-006 | 6.10
E08 | Product – Expire Product | US-8.06 | As a system, I want to notify and auto-unpublish expired products (configurable) so that expired products are never sold. | 1. Daily job flags Near Expiry and Expired and sends notifications 2. Expired products cannot be sold (BR-05) 3. Auto-unpublish can be switched off | Should | R2 | Backend Dev, QA Engineer | 0 | 16 | 5 | 0 | 21 | FR-EXP-005, BR-05 | 3.05
E09 | Order Management | US-9.01 | As an order manager, I want an order list (Order No., customer, product, total NPR, payment method, status, created, action) so that I track all orders. | 1. Created time is shown in NPT, readable format 2. Multi-item orders show all items or "n items" with drill-down 3. Pagination and empty state work | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 20 | 14 | 7 | 0 | 41 | FR-ORD-001, 002, 006 | 1.03
E09 | Order Management | US-9.02 | As an order manager, I want search, filter and sort orders so that I find orders fast. | 1. Filter by status, payment method, date range, customer 2. Search by order number and customer | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 10 | 5 | 0 | 25 | FR-ORD-003 | 9.01
E09 | Order Management | US-9.03 | As an order manager, I want Export and Bulk Action on orders so that I process batches. | 1. Export downloads current filter in CSV/XLSX 2. Bulk status update for selected orders | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 10 | 4 | 0 | 18 | FR-ORD-003 | 9.01
E09 | Order Management | US-9.04 | As an order manager, I want a status lifecycle with history so that fulfilment is controlled and traceable. | 1. Pending → Confirmed → Packed → Shipped → Delivered; also Cancelled, Returned, Refunded 2. Invalid transitions are blocked 3. Each change logs user and time | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 16 | 8 | 0 | 34 | FR-ORD-005 | 9.01
E09 | Order Management | US-9.05 | As an order manager, I want View, Update Status and Cancel in the action menu so that I can act on an order. | 1. Cancel allowed only before Shipped (BR-07) 2. View shows items, address, payment and history | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 16 | 10 | 6 | 0 | 32 | FR-ORD-007, BR-07 | 9.04
E09 | Order Management | US-9.06 | As an order manager, I want to print an invoice so that customers receive documents. | 1. PDF shows order, items, NPR totals, tax, store details | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 4 | 12 | 4 | 0 | 20 | FR-ORD-007 | 9.05
E09 | Order Management | US-9.07 | As an order manager, I want to create an order manually (customer, items, payment, address) so that phone and walk-in orders are captured. | 1. Customer and products searchable; totals auto-calculate 2. Order is saved with Pending status | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 24 | 16 | 8 | 0 | 48 | FR-ORD-004 | 9.01
E09 | Order Management | US-9.08 | As a system, I want payment method and status synced from Khalti and eSewa so that order payment state is accurate. | 1. Webhook updates payment status; failed callbacks are retried 2. Payment reference is stored on the order | Should | R2 | Backend Dev, QA Engineer | 0 | 24 | 8 | 0 | 32 | Payment dependency (scope to confirm) | 9.01
E10 | Vendor Management | US-10.01 | As a vendor manager, I want a vendor list (name, email, phone, category, location, joined, status, action) so that I see all sellers. | 1. Empty state "No vendors found" 2. Pagination works | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 8 | 5 | 0 | 25 | FR-VEN-001 | 1.03
E10 | Vendor Management | US-10.02 | As a vendor manager, I want to add a vendor with business and contact details so that sellers can be onboarded. | 1. All basic fields are mandatory 2. Email format, +977 phone, unique email/phone/registration no./PAN are validated | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 12 | 7 | 0 | 33 | FR-VEN-002, 005 | 10.01
E10 | Vendor Management | US-10.03 | As a vendor manager, I want to upload business documents (Registration, PAN/VAT, TIN) in Business and Company tabs so that compliance is verified. | 1. PNG/JPG/WEBP/PDF up to 50 MB; all three documents required 2. Documents can be previewed by authorised roles | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-VEN-003 | 1.04
E10 | Vendor Management | US-10.04 | As a vendor manager, I want bank details captured and protected so that settlements are accurate and secure. | 1. Bank, account name, number, branch are mandatory 2. Data is encrypted at rest; account number masked in UI 3. Only authorised roles can reveal | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 14 | 6 | 0 | 28 | FR-VEN-004, 008 | 10.02
E10 | Vendor Management | US-10.05 | As a vendor manager, I want to approve, reject (with reason) or suspend vendors so that only verified vendors sell. | 1. New vendors default to Pending Verification 2. Rejection needs a reason; vendor is notified 3. Unapproved vendors cannot publish products | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 12 | 14 | 7 | 0 | 33 | FR-VEN-006, BR-06 | 10.02
E10 | Vendor Management | US-10.06 | As a vendor manager, I want search, filter, sort and bulk actions on vendors so that I manage many sellers. | 1. Filter by status, category, location, joined date 2. Bulk suspend/export available | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 8 | 4 | 0 | 20 | FR-VEN-007 | 10.01
E11 | Customer Management | US-11.01 | As a support agent, I want a customer table with loading and empty states so that I can see all customers. | 1. Columns S.N, customer, email, phone, status, registered on, total orders, action 2. Empty state "No customers found" 3. Server-side pagination | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-CUS-01, 05, 06 | 1.03
E11 | Customer Management | US-11.02 | As a support agent, I want to search customers by name, email or phone so that I find a customer quickly. | 1. Debounced search from 2 characters 2. Combines with filter and sort | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 6 | 3 | 0 | 13 | FR-CUS-02 | 11.01
E11 | Customer Management | US-11.03 | As a support agent, I want to sort customers ascending or descending so that I can order the list. | 1. Sort dropdown has Ascending and Descending; default field is registration date 2. Field selector (name, date, orders) available | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 4 | 2 | 0 | 10 | FR-CUS-03 | 11.01
E11 | Customer Management | US-11.04 | As a support agent, I want a filter panel (status, registration date, city/district) so that I narrow the list. | 1. Filters combine with search and sort 2. One-click clear all | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 10 | 8 | 4 | 0 | 22 | FR-CUS-04 | 11.01
E11 | Customer Management | US-11.05 | As a support agent, I want a customer profile with details, addresses, orders and tickets so that I can help the customer. | 1. Profile opens from the action column 2. Order history links to order detail | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 16 | 12 | 6 | 0 | 34 | FR-CUS-07 | 11.01
E11 | Customer Management | US-11.06 | As an admin, I want to block or unblock a customer so that abusive accounts are controlled. | 1. Blocked customers cannot log in or order (BR-08) 2. Action is audited | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 4 | 10 | 5 | 0 | 19 | FR-CUS-08, BR-08 | 11.01
E11 | Customer Management | US-11.07 | As an admin, I want to export the filtered customer list so that data can be used for reports. | 1. CSV/XLSX export respects current filters and permissions | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 2 | 8 | 3 | 0 | 13 | FR-CUS-09 | 11.01
E11 | Customer Management | US-11.08 | As a super admin, I want customer data limited by role with audited access so that personal data is protected. | 1. Customer Support is view-only 2. Views of personal data are logged | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 2 | 10 | 4 | 0 | 16 | FR-CUS-10, NFR-09 | 2.02
E12 | CMS – Web Management & Media | US-12.01 | As a content manager, I want to edit Home Hero fields (section name, hero text, subtitle) so that the homepage message is current. | 1. Section Name and Hero Text are required (max 100/150); Subtitle max 300 2. Inputs are enabled, not greyed (fixes F-05) | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-HOM-01, 02 | 1.03
E12 | CMS – Web Management & Media | US-12.02 | As a content manager, I want repeatable lists for Marketplace Text, Supporting Text and Marketplace Roles so that hero copy can be extended. | 1. Add, edit, remove and reorder entries | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 6 | 5 | 0 | 25 | FR-HOM-03 | 12.01
E12 | CMS – Web Management & Media | US-12.03 | As a content manager, I want service highlight cards so that key services are shown on the homepage. | 1. Card has icon/image, title*, description, link 2. Add, edit, remove, reorder; empty text "No services added yet." | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 16 | 10 | 6 | 0 | 32 | FR-HOM-04 | 12.01
E12 | CMS – Web Management & Media | US-12.04 | As a content manager, I want a section banner upload with preview so that the hero has a visual. | 1. JPG/PNG/WebP up to 2 MB with preview, replace and remove 2. Recommended size is shown | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 4 | 3 | 0 | 15 | FR-HOM-05 | 1.04
E12 | CMS – Web Management & Media | US-12.05 | As a content manager, I want Create then Save Changes behaviour and Cancel confirmation so that I do not lose or duplicate content. | 1. Single record; button reads Save Changes after first save 2. Cancel with unsaved changes asks for confirmation | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 6 | 4 | 3 | 0 | 13 | FR-HOM-06, 08 | 12.01
E12 | CMS – Web Management & Media | US-12.06 | As a content manager, I want saved CMS content to appear on the storefront without deployment so that updates go live quickly. | 1. Public CMS API serves Home, About and other pages 2. Cache refresh ≤ 5 minutes | Must | R1 – MVP | Backend Dev, QA Engineer | 0 | 12 | 4 | 0 | 16 | FR-HOM-07 | 12.01
E12 | CMS – Web Management & Media | US-12.07 | As a content manager, I want to manage the About page (title, description, image) so that visitors learn about Hamro Mall. | 1. Title required (max 100); inline error if empty 2. Existing content loads on open; thumbnail with replace/remove 3. About and General Settings use separate data (fixes F-04) | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 8 | 6 | 0 | 28 | FR-ABT-01, 02, 04, 05 | 1.04
E12 | CMS – Web Management & Media | US-12.08 | As a content manager, I want a rich-text editor with sanitised output so that content can be formatted safely. | 1. Bold, lists, links supported 2. Scripts and unsafe HTML are stripped on save | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 8 | 6 | 4 | 0 | 18 | FR-ABT-03, FR-CMS-03 | 12.07
E12 | CMS – Web Management & Media | US-12.09 | As a content manager, I want a media list with search, filter and sort so that I find files fast. | 1. Columns S.N, FileName, Extension, Name, Size, Type, Action 2. Empty state "No media found" 3. Filter by type and date | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 10 | 6 | 0 | 30 | FR-MED-01, 02 | 1.04
E12 | CMS – Web Management & Media | US-12.10 | As a content manager, I want to upload a file and have metadata filled automatically so that I do not type URL, path, MIME or size. | 1. Uploading fills File Name, URL, Path, MIME, Extension and Size as read-only 2. Type dropdown defaults to IMAGE; invalid files are rejected 3. Manual entry only via advanced option | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 14 | 14 | 7 | 0 | 35 | FR-MED-03, 04, 05, F-06 | 1.04
E12 | CMS – Web Management & Media | US-12.11 | As a content manager, I want preview, edit metadata, copy URL and delete media so that I can maintain the library. | 1. Delete is blocked or warned if media is used by a CMS page | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 10 | 10 | 5 | 0 | 25 | FR-MED-06 | 12.09
E12 | CMS – Web Management & Media | US-12.12 | As a content manager, I want bulk select and delete media so that cleanup is faster. | 1. Header checkbox and bulk delete with confirmation | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 4 | 6 | 3 | 0 | 13 | FR-MED-07 | 12.09
E12 | CMS – Web Management & Media | US-12.13 | As a content manager, I want to pick existing media from upload zones so that files are reused. | 1. Upload zones offer "Choose from library" with search | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 12 | 2 | 4 | 0 | 18 | FR-MED-08 | 12.09
E12 | CMS – Web Management & Media | US-12.14 | As a content manager, I want to manage Breadcrumb header banners so that inner pages have branded headers. | 1. List of pages with title, image, status; edit and save | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 10 | 8 | 5 | 0 | 23 | §4.3.4 (provisional) | 12.09
E12 | CMS – Web Management & Media | US-12.15 | As a content manager, I want to manage promotional banners with schedule so that campaigns are visible when needed. | 1. CRUD with image, link, placement, start/end, order, status 2. Banner shows only within schedule when Active | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 16 | 12 | 6 | 0 | 34 | §4.3.4 (provisional) | 12.09
E12 | CMS – Web Management & Media | US-12.16 | As a content manager, I want to write and publish blog posts so that content marketing drives traffic. | 1. CRUD with title, slug, cover, rich content, category/tags, SEO meta 2. Draft and Publish states; slug unique | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 28 | 20 | 10 | 0 | 58 | §4.3.4 (provisional) | 12.08
E12 | CMS – Web Management & Media | US-12.17 | As a content manager, I want to manage testimonials so that social proof is shown. | 1. CRUD with name, designation, photo, rating, message, status, order | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 12 | 10 | 5 | 0 | 27 | §4.3.4 (provisional) | 12.09
E12 | CMS – Web Management & Media | US-12.18 | As a content manager, I want to manage FAQs by category so that customers find answers. | 1. CRUD with category, question, answer, order, status | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 12 | 10 | 5 | 0 | 27 | §4.3.4 (provisional) | 12.01
E12 | CMS – Web Management & Media | US-12.19 | As a content manager, I want to edit contact details and handle enquiries so that customers can reach us. | 1. Edit address, phone, email, map link, hours 2. Enquiry inbox with status and reply | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 18 | 14 | 7 | 0 | 39 | §4.3.4 (provisional) | 12.01
E12 | CMS – Web Management & Media | US-12.20 | As a marketing manager, I want to manage marketing campaigns so that promotions are organised. | 1. CRUD campaign with audience, period, offer link, status 2. Performance summary per campaign | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 24 | 20 | 9 | 0 | 53 | §4.3.4 (provisional) | 12.15
E12 | CMS – Web Management & Media | US-12.21 | As a content manager, I want CMS content to publish only when Active and in schedule so that unfinished content never goes live. | 1. Inactive or out-of-schedule items are excluded from public API 2. Common toolbar, table and status toggle used on all CMS lists | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 4 | 8 | 4 | 0 | 16 | FR-CMS-01, 02, BR-05 | 12.06
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.01 | As an admin, I want to edit General Settings (title, description, image) so that platform identity is controlled. | 1. Title required; Save Changes persists 2. Changes appear in admin and storefront without redeploy | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 10 | 8 | 5 | 0 | 23 | FR-SET-01, 03 | 1.04
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.02 | As an admin, I want extra general fields (logo, favicon, contact, address, social, language, time zone, currency) so that settings cover real operations. | 1. Fields validate (email, phone, URL) 2. Default time zone Asia/Kathmandu; currency NPR | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 8 | 4 | 3 | 0 | 15 | FR-SET-02 | 13.01
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.03 | As an admin, I want to maintain policies (Terms, Privacy, Return, Shipping) with versions so that legal pages stay current. | 1. Rich text with version date and publish status 2. Storefront shows latest published version | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 14 | 12 | 5 | 0 | 31 | FR-SET-04 | 12.08
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.04 | As a super admin, I want security settings (password rules, session timeout, 2FA, lockout, IP allow-list) so that the panel is hardened. | 1. Only Admin can open Security 2. Rules apply at next login 3. 2FA enrolment works for admin users | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 16 | 20 | 8 | 0 | 44 | FR-SET-05 | 2.01
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.05 | As an admin, I want to manage currencies and exchange rates so that pricing can support more than NPR. | 1. Exactly one default currency; default cannot be deleted 2. Rate history is kept | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 12 | 12 | 6 | 0 | 30 | FR-SET-06, BR-07 | 13.01
E13 | Settings (General, Policy, Security, Currency, Subscriber) | US-13.06 | As a marketing manager, I want a subscriber list with export and unsubscribe so that newsletters respect consent. | 1. Search, filter, export, delete 2. Unsubscribed emails are excluded from sends | Could | R3 | Frontend Dev, Backend Dev, QA Engineer | 10 | 10 | 5 | 0 | 25 | FR-SET-07 | 1.03
E14 | Non-Functional Hardening, Testing & Release | US-14.01 | As an user, I want list pages to load within 3 seconds for 10,000 records so that the panel feels fast. | 1. Server-side pagination, search, sort with indexes 2. Saves complete within 2 seconds 3. Load test report signed off | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer, DevOps Engineer | 8 | 24 | 12 | 4 | 48 | NFR-03 | All lists
E14 | Non-Functional Hardening, Testing & Release | US-14.02 | As a security officer, I want security hardening and penetration test fixes so that data and users are protected. | 1. No critical or high findings open 2. TLS 1.2+, CSRF/XSS/injection protections verified 3. Vendor bank and document data encrypted at rest | Must | R1 – MVP | Backend Dev, QA Engineer, DevOps Engineer | 0 | 24 | 12 | 8 | 44 | NFR-01, 02, FR-VEN-008 | All modules
E14 | Non-Functional Hardening, Testing & Release | US-14.03 | As an user, I want accessible, cross-browser screens so that everyone can use the panel. | 1. WCAG 2.1 AA checks pass; icon buttons have labels/tooltips (F-11) 2. Works on latest Chrome, Edge, Firefox, Safari; tablet width | Should | R2 | Frontend Dev, QA Engineer | 24 | 0 | 16 | 0 | 40 | NFR-06, 07, F-11 | All modules
E14 | Non-Functional Hardening, Testing & Release | US-14.04 | As an operator, I want Nepal formats and Unicode content so that local data displays correctly. | 1. Dates in NPT, amounts in NPR 2. Nepali text saves and displays without corruption | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 8 | 6 | 4 | 0 | 18 | NFR-11, FR-ORD-002 | All modules
E14 | Non-Functional Hardening, Testing & Release | US-14.05 | As a developer, I want automated unit, API and end-to-end tests so that regressions are caught early. | 1. Core flows (login, role CRUD, product publish, order status, vendor approval) covered end to end 2. Suite runs in CI on every merge | Should | R2 | Frontend Dev, Backend Dev, QA Engineer | 24 | 24 | 40 | 0 | 88 | NFR-10 | 1.01
E14 | Non-Functional Hardening, Testing & Release | US-14.06 | As a project team, I want SIT/UAT support and defect fixing so that the client can sign off. | 1. Critical and high defects closed; medium agreed 2. UAT sign-off recorded | Must | R1 – MVP | Frontend Dev, Backend Dev, QA Engineer | 40 | 40 | 30 | 0 | 110 | — | All modules
E14 | Non-Functional Hardening, Testing & Release | US-14.07 | As an operator, I want production deployment, monitoring, backups, runbook and admin training material so that the system is supportable. | 1. Monitoring and alerts live; daily backups tested by restore 2. Runbook and user guide delivered | Must | R1 – MVP | Backend Dev, QA Engineer, DevOps Engineer | 0 | 6 | 4 | 24 | 34 | NFR-04 | 14.06
|  |  | TOTAL |  |  |  |  | 1272 | 1188 | 687 | 68 | 3215